Monthly Member-Service Leadership Product: Delivery Plan & Stakeholder Approach

PM-1, PM-2 and PM-3  ·  Round 1 BI Analyst assessment  ·  Prepared by Piyush  ·  October 2026

# PM-1 · Implementation plan

Goal: turn the Round 1 analysis and dashboard into a trusted monthly leadership product (dashboard + KPI pack + alerts), live in about 10 weeks, with clear ownership afterwards.

| Phase (weeks) | Key activities | Deliverable / exit criteria | Owner |
| --- | --- | --- | --- |
| 1. Requirements & discovery (wk 1–2) | Interview VP Member Service, Ops managers, WFM, QA, CX. Agree the 3–5 decisions the product must support (e.g. "where do we add capacity this month?"). Inventory sources: interactions, members, targets, WFM, survey. | Signed requirements: decisions, audiences, refresh frequency, KPI shortlist | BI Analyst (lead), VP Member Service (sponsor) |
| 2. Metric definitions (wk 2–3) | Finalize KPI dictionary: formula, population, exclusions, direction, target, owner. Resolve open items: 90s service level, abandonment target, same-reason repeat, satisfaction scale. | Approved metric dictionary (version 1.0) and target sign-off | BI Analyst; KPI owners approve |
| 3. Data validation (wk 3–5) | Move the SQL pipeline (raw → staging → analysis) into the governed warehouse. Automate the controls from PY-3 (schema, duplicates, unmapped categories, referential integrity, volume swings). Reconcile 3 months against source systems and the finance contact count. | All controls automated; reconciliation within ±0.5% | BI / Data Engineering; source system owners |
| 4. Development (wk 4–7) | Build the dashboard in the standard BI tool (Power BI): KPI tiles, trend vs target, attention list, driver drill-down, limitations panel. Row-level security if team or agent views are added. Productionize the KPI pack and weekly hot-spot alerts. | Dashboard and pack in a test workspace; peer-reviewed SQL/DAX | BI Analyst; BI peer reviewer |
| 5. UAT (wk 7–8) | Scripted tests: numbers match the certified extract; drill paths work; filters cross-check. Executive walkthrough: can a leader answer "what needs attention, and why?" in under 2 minutes? Log and fix defects; regression retest. | UAT sign-off by sponsor and 2 Ops managers; zero open severity-1 defects | Business testers; BI fixes |
| 6. Launch (wk 9) | Publish to production workspace; schedule refresh. Present the first live pack at the monthly leadership meeting. Hypercare: daily checks for 2 weeks. | First production cycle delivered on time | BI Analyst; VP Member Service |
| 7. Documentation & training (wk 8–10) | One-page user guide; KPI dictionary inside the dashboard; 30-minute training for leaders and Ops. Runbook: refresh steps, controls, failure handling, contacts. | Guide, runbook and recorded training published | BI Analyst |
| 8. Refresh process (ongoing) | Monthly: data lands by business day 2 → controls run automatically → pack published by business day 3. Weekly: hot-spot alert run. Any FAIL control stops publication and notifies the data owner. | Monthly SLA met (published by business day 3, ≥ 95% of months) | BI (run), Data owner (fix) |
| 9. Ongoing ownership (ongoing) | Product owner: BI Analyst. Business owner: VP Member Service. Each KPI has a named owner. Quarterly review: retire unused visuals, recheck targets and thresholds, check usage. Change requests through a simple intake and prioritization log. | Quarterly review held; usage and data-quality metrics reported | BI Manager; VP Member Service |

# PM-2 · Dependencies, risks, decisions, controls and communication

## Major dependencies

- Data access: a scheduled, governed extract of interactions and members (today a manual file); WFM and survey data for the next phase.

- Decisions on targets: the 90s service level, abandonment and repeat targets need sign-off before build (phase 2).

- BI platform: a Power BI workspace, gateway and refresh schedule; security group for leaders.

- People: time from Ops managers and QA for UAT and the outcome-code audit; a data engineer for pipeline hardening.

## Project risks

| Risk | Likelihood / impact | Mitigation | Owner |
| --- | --- | --- | --- |
| Metric definitions disputed late (e.g. what counts as "resolved") | Medium / High | Lock the dictionary in phase 2 with sponsor sign-off; changes go through the change log | BI Analyst |
| Source data quality worsens (new categories, duplicates, missing fields) | Medium / High | Automated controls with FAIL stops; data-owner SLA; control results visible in the pack | Data owner |
| Satisfaction scale cannot be confirmed | Medium / Medium | Show satisfaction as trend-only with n and a caution flag until resolved | CX Lead |
| Scope creep (more metrics, more views) | High / Medium | Decision-based scope; quarterly backlog review; see PM-3 | BI Analyst + Sponsor |
| Low adoption by leaders | Medium / High | Co-design in discovery; attention list on page one; use the pack in the monthly meeting | Sponsor |
| Key-person dependency on one analyst | Medium / Medium | Runbook, peer-reviewed code in version control, backup owner trained | BI Manager |

## Stakeholder decisions required

| Decision | Decision maker | Needed by |
| --- | --- | --- |
| Approve the KPI shortlist and add the service-level and abandonment targets | VP Member Service | End of week 3 |
| Satisfaction: confirm scale and method; keep as target or trend-only | CX Lead + VP Member Service | End of week 3 |
| Adopt same-reason repeat; commission the outcome-code QA audit | QA Lead + VP Member Service | Week 4 |
| Alert thresholds and who receives weekly hot-spot alerts | Ops Manager | Week 6 |
| Production access, security groups, data retention | IT / Data Governance | Week 6 |

## Controls to sustain the solution

- Data controls: schema, duplicates, category mapping, referential integrity, completeness, volume-swing checks on every run (PASS / WARN / FAIL; FAIL blocks publication).

- Reconciliation: monthly total contacts reconciled to the source-system count; KPI pack reconciled to the dashboard.

- Change control: SQL, DAX and Python in version control with peer review; metric dictionary versioned; changes logged and announced.

- Access & privacy: role-based access, no member-level data in leadership views, no external sharing links.

- Quality monitoring: refresh success, on-time publication, control failures and dashboard usage reported quarterly.

## Communication plan

| What | Audience | When / how |
| --- | --- | --- |
| Kickoff: goals, scope, timeline, decisions needed | Sponsor, Ops, WFM, QA, CX, IT | Week 1, 45-minute meeting + one-page charter |
| Progress, upcoming decisions, blockers, risk status (RAG) | Sponsor + core stakeholders | Weekly 15-minute check-in + short written status |
| Decision requests | Named decision maker | As needed, in writing with options and a recommendation; tracked in the decision log |
| Blockers or red risks | Sponsor | Within 24 hours, with impact and proposed fix (no waiting for the weekly) |
| Demo of working build | Sponsor + UAT testers | End of weeks 5 and 7 |
| Launch note and training | All users | Week 9 |
| Post-launch: release notes, quarterly review | Users + sponsor | Each change; quarterly |

# PM-3 · Stakeholder scenario: the executive who wants 25 metrics

Situation. An executive asks for a dashboard with 25 metrics. My analysis suggests a smaller set drives decisions. My goal is a product the executive uses and trusts, not to win the argument.

## 1. Start with their need, not the list

I would set up a 30-minute conversation and ask what decisions they make each month, what questions they get from their own leadership, and what went wrong last time they were caught off guard. Usually 25 metrics are a proxy for "I don't want to be surprised." I would take the list seriously: every metric on it reflects a concern, and I want to understand each one.

## 2. Validate with evidence

I would map each of the 25 metrics to a decision or question, and check three things: (a) does it change, or is it flat? (b) does it duplicate another metric? (c) does anyone act on it? In this dataset, for example, the any-reason repeat rate mostly duplicates volume, and average wait alone hid the May failure. Showing that kind of concrete example is more persuasive than a general principle.

## 3. Recommend a layered approach, not a rejection

- Page 1 (executive): 6–8 KPIs tied to decisions, each with target, trend and status, plus an automatic "what needs attention" list. This answers "am I going to be surprised?"

- Page 2 (diagnostic): the drill-down and driver views, where many of the remaining metrics live as breakdowns rather than tiles.

- Appendix / data table: all 25 metrics, available for anyone who wants them, without crowding the decision view.

Nothing they asked for disappears; it moves to the layer where it is useful. I would show a quick mock-up of both versions side by side so the trade-off is visible.

## 4. Make it reversible and measurable

I would propose a 2-cycle trial of the focused version, with an agreement to promote any metric back to page 1 if it was needed for a decision during the trial. I would track which views get used. After two cycles we review together, so the decision rests on their experience rather than my opinion.

## 5. Maintain the relationship

I would acknowledge their experience: they often know about issues the data does not show. I would follow up in writing with what we agreed, and credit their input when the dashboard catches the next problem early. If they still want all 25 on page one after the trial, it is their product. I would build it, keep the attention list at the top, and document my recommendation. Disagreeing respectfully and then committing to the decision keeps trust for the next conversation.